## MVPFeatures
List of capabilities | Assignment / Deadline
- Set base knowledge of Hydrogen | 2023-07-15
-- Need database of inputs and/or documents (oil & gas focused first: CCUS, biofuels, RECs/PPAs, incentives, legal/regulation, transportation, storage, solar, wind, geothermal, nuclear…)
-- TO DO: Add more knowledge, make list of agencies, consultants, sources
- Current Knowledge of (Policies, funding announcements, projects, …) | 2023-07-15
-- Data sources: DOE RSS feeds, FOAs, useful public dataset
- Given string of questions, questions from reports, recommend other relevant prompts.
-- After each prompt, provide a list of three relevant prompts. | Mark to work on next
- Read/input text AND/OR images from any PDF, Excel/CSV, URL
-- Which LLM brings back images from reports? Look at Azure Cognitive Services
- Verify with user whether output is accurate and update future answers. | Contractor
-- Refine knowledge through user feedback which is in the form of them providing PDFs or URLs
-- Verify/vet/re-learn from user-input, making it a HIGHLY trustworthy source
-- Award tokens (Karma) for flagging errors and suggesting new, community-accepted answers. In return, they will be firs to be invited to test new features.
-- This must be able to cross-reference at least three other sources that come to similar conclusions
- Other possible activities in future version:
- Agent-based game theory simulation
- Think like succesful energy investors
- Create an agent to respond to similar requests
- Create X number of slides in presentation or document, with images and text from reports including their references.
- Consider other topics. Should somehow be very relevant to hydrogen such as competiting technologies.
-- Li-ion batteries
-- Carbon capture, utilization, and sequestration
-- Better material on policy and credits (45V and 45Q)
Bold: Key activity map activities

## Sources
No. | Name | URL
1 | NREL
2 | ANL
3 | IRENA
4 | CARB
5 | DOE
6 | IRS
7 | EPA
8 | LinkedIn - H2 forums
9 | Reddit - H2 news
10
11
12
13
14
15
16
17
18
19
20

## DailyRoutineWeeklyGoal
NREL Days
6:45-7:15 am | Strategize for the day, take notes, set daily objective
8:00 - 11:00 pm | Work on project in 2 x 50 min chunks
Non-NREL Work Days
6:45-7:15 am | Strategize for the day, take notes, set daily objective
8:00 am - 12:00 pm | Work in 45 min batches
12:00 pm - 1:30 pm | Lunch / Walk / Bike / Workout
1:30 - 5:00 pm | Work in 45 min batches
5:00 pm to 8:00 pm | Kids/family
8:00 pm to 11:00 pm | Work in 45 min batches

## ActivityMap
Chatbot features with accurate, doman-specific knowledge: hydrogen energy tech
Up-to-date knowledge on hydrogen
Suggests related prompts based on user's prompt history or commonly asked questions
Provides citations of results. Allows community to challenge them to improve
Return relevant graphs/images of input prompt
Retains knowledge state throughout interaction with user
Incorporates knowledge from oil & gas industry and related tangential industries
Activity Map = decarbX_v1
Users suggest new sources
Users awarded token for initial suggestions
Users awarded larger amount of tokens (or karma) once three others verify source
Fluid and fast interaction with user
More tokens allowed and cheaper than ChatGPT
uncertain
Hydrogen TEA
production
transmission
end uses
carriers
policy
regulation
integrated systems
storage
Solar TEA
Wind TEA
Nuclear TEA
Natural Gas TEA
Hydro TEA
Biomass TEA
Natural Gas Infrastructure
CCU/CCUS
Electric Grid

## DailyNotes
Date | Notes | Status | Due Date | DONE | IN PROGRESS | PRIORITY
2023-07-16 | Created pitch deck, updated business plan, thought more about Year 2. | DONE
2023-07-15 | Remade connection to Pinecone in the script. Not sure GPT is giving back proper results so trying to make sure the LLM is in fact pulling from the knowledge base in Pinecone's vectorDB. Next step is to verify this and then start to break down accuracy of questions | IN PROGRESS
2023-07-14 | Fixed Estuary/Pinecone connection and vectorDB, however, I think the vectoDB is overwhelming OpenAI limits. May have to upgrade. Still need to figure out how to set primary key. Updated business plan. Read ProcessGPT paper | IN PROGRESS
2023-07-13 | Attended AITransformationSummit by Pinecone/MS in San Fran. Really useful. Good to know I'm roughly even with others developing tools right now. | DONE
2023-07-12 | Added more to the business plan. Updated H2 knowledge database now with 200 files, trying to get into Pinecone but seeing Materialization error. Bought tickets to Pinecone AI summit. Better meet some folks, find a Dev co-founder or talk to Jamie next. | DONE
2023-07-11 | Talked with John C. Got some great ideas. Need a team of 3 founders. Need to better define the problem, the solution, customer, addressable market size | DONE
2023-07-10 | Updated activity map, MVP features. Spoke with Kamal about product. Mentioned being able to introduce me to developers in US or in India | DONE
2023-07-09 | Create new version of Flow and try different Embedding API (didn't work). Instead changed the embedding model in Estuary. Tomorrow play with query to see how results look. | DONE
2023-07-08 | Created workflow diagram to understand how information flows, what companies/algorithms/modules do what and how best to leverage the best in class in each | DONE
2023-07-07 | Spent time understnaind embedding and vectorDBs. Need to find an alternative to OpenAI's embedding model. Cohere's embedding model is interesting. Multilingual and data-oriented (bring model to data). Weaviate also an interesting alternative vectorDB | IN PROGRESS
2023-07-06 | Jenny fixed my Estuary schema. Materialization worked and published! However, first query gave back strange answer | DONE
2023-07-05 | Tried Jenny's suggestions. Responded with email with my error messages and asked her to setup for me. Worked more on contractor's SOW. Think it is now near final. Need to focus shift to the AI model now to make sure it offers more value than ChatGPT. | DONE
2023-07-04 | Researched how to prevent hallucination and added citations as output. Enhanced activity map. | DONE
2023-07-03 | Worked on estuary connection, still no luck. Added to activity map. | DONE
2023-07-02 | Finish connection to estuary and contractor document | DONE
2023-07-01 | Briefly reserached developers -> Need to identify at least 5. | IN PROGRESS
2023-06-30 | rest the mind
2023-06-29 | Continued working on input file for Estuary. Created a JSON and got feedback from Jenny on what to do next | DONE
2023-06-28 | Created a Parquet file from PDF data. Working on setting up the data feed pipelie for embeddings and vectorization in Pinecone and Estuary | DONE | 2023-06-29
2023-06-27 | Saved and published new data connector from Estuary Flow to Google Cloud | DONE
2023-06-26 | - Researched python loops to verify data using ChatGPT. Narrowed down to 2 methods. | IN PROGRESS
2023-06-25 | - Refine contractor's SOW after spend a few days working on algo myself. | IN PROGRESS | 2023-07-03
2023-06-25 | - Send SOW for bids to 3 contractors | IN PROGRESS | 2023-07-10
2023-06-24 | - Need more prompts to enhance output. How will initial users be using this? Only way to find out is to create web interface to get more interaction. | IN PROGRESS
2023-06-24 | - Cannot do financial calcs from 10Ks. BloomberGPT is an LLM. | DONE
2023-06-24 | - Add other documents that complement H2 TEA - (oil & gas focused first: CCUS, biofuels, RECs/PPAs, incentives, legal/regulation, transportation, storage, solar, wind, geothermal, nuclear...) | Priority
2023-06-24 | - Get Pinecone and Estuary setup for vectorstor DB and read two articles on Chrome. Research more into vectorstores | DONE
2023-06-23 | - Trying to get better answers by playing with vectorDB. Possible the DirectoryLoad method is overloading the LLM | DONE
2023-06-23 | -- LLM seems to be getting back better answers, but all dependent on highly specific prompt. | DONE
2023-06-23 | - Loaded 13 more NREL reports in H2 directory (100 MB of data). Will try to ask a variety of questions related to hydrogen. | DONE
2023-06-23 | -- Get input data up towards 1 GB. Need to add other aspects of H2 like: materials, supply chain [added 3], chemistry, integrated systems [added 1] | IN PROGRESS
2023-06-23 | -- Questions seem to be resulting in good answers. | DONE
2023-06-23 | -- Not able to answer specific technical potential questions. Might be because can't access raw data | IN PROGRESS
2023-06-22 | Watch L5 | DONE
2023-06-22 | Try to add two documents to doc loader and retrieve answers from two | DONE

## WorkFlow
[Estuary Flow,
Cohere,
Hugging Face, OpenAI, many more...]
Results
VectorDB API
Embedding API
Raw Data
LLM Application
User Prompt
Raw data to be embedded
Embedded data to be vectorized
Requests
Query
Results
[LangChain (framework),
ChatGPT
Cohere,
many more...]
[Pinecone, Chroma, Deep lake, FAISS,
many more....]
[Google Cloud Storage: input.json]
PyPDF load/split into JSON
Retriever
Knowledge Update
[Google Docs]
Raw Data Web Scraper
[Python]
User

## QuestionsFollowUp
1 | What to do when eval_chain.evaluate and QAEvalChain gives back INCORRECT answers?
2 | How to change the sources the LLM uses?

## HelpfulDocumentation
https://python.langchain.com/docs/modules/data_connection/
RetrievalQA works with both the vectorstores and the chain
- Keep text input to no more than 10-15 lines to control how many tokens being sent to LLM. -> should be vetted further.
"Agents" are a way to control what data is called when given prompt

## AdditionalFeatures
- Load transcripts from webpages, company websites, YouTube video transcripts
- Load private documents, analyze and keep queries proprietary

## UseCases
- High level understanding
- Run high level economics
- Understand/summarize policy
User Types:
- Analysts
- Directors
- C-suite
- Researchers
- Casual users

## Monetization
Market Segmentation:
- Casual User
- Advanced User
- Pro User
When signing people up, testing audience:
- Create artificial wait list when signing up
- Take credit card number when signing up. 14 days free trial period.