## DailyNotes
Date | Notes | Status | Due Date | DONE | IN PROGRESS | PRIORITY
2023-06-28 | Created a Parquet file from PDF data. Working on setting up the data feed pipelie for embeddings and vectorization in Pinecone and Estuary | IN PROGRESS | 2023-06-29
2023-06-27 | Saved and published new data connector from Estuary Flow to Google Cloud | DONE
2023-06-26 | - Researched python loops to verify data using ChatGPT. Narrowed down to 2 methods. | IN PROGRESS
2023-06-25 | - Refine contractor's SOW after spend a few days working on algo myself. | IN PROGRESS | 2023-07-03
2023-06-25 | - Send SOW for bids to 3 contractors | IN PROGRESS | 2023-07-10
2023-06-24 | - Need more prompts to enhance output. How will initial users be using this? Only way to find out is to create web interface to get more interaction. | IN PROGRESS
2023-06-24 | - Cannot do financial calcs from 10Ks. BloomberGPT is an LLM. | IN PROGRESS
2023-06-24 | - Add other documents that complement H2 TEA - (solar, wind, CCUS, biofuels, geothermal, nuclear, PPAs, incentives, legal, transportation, storage, ...) | Priority
2023-06-24 | - Get Pinecone and Estuary setup for vectorstor DB and read two articles on Chrome. Research more into vectorstores | Priority
2023-06-23 | - Trying to get better answers by playing with vectorDB. Possible the DirectoryLoad method is overloading the LLM | DONE
2023-06-23 | -- LLM seems to be getting back better answers, but all dependent on highly specific prompt. | DONE
2023-06-23 | - Loaded 13 more NREL reports in H2 directory (100 MB of data). Will try to ask a variety of questions related to hydrogen. | DONE
2023-06-23 | -- Get input data up towards 1 GB. Need to add other aspects of H2 like: materials, supply chain [added 3], chemistry, integrated systems [added 1] | IN PROGRESS
2023-06-23 | -- Questions seem to be resulting in good answers. | DONE
2023-06-23 | -- Not able to answer specific technical potential questions. Might be because can't access raw data | IN PROGRESS
2023-06-22 | Watch L5 | DONE
2023-06-22 | Try to add two documents to doc loader and retrieve answers from two | DONE

## DailyRoutine
NREL Days |  | Features to work on in order:
6:45-7:15 am | Strategize for the day, take notes, set daily objective | 1) Input data pipeline (Estuary, Pinecone)
8:00 - 11:00 pm | Work on project in 2 x 50 min chunks | 2) Training data on MORE H2 documents
3) Build Web app interface
Non-NREL Work Days
6:45-7:15 am | Strategize for the day, take notes, set daily objective
8:00 am - 12:00 pm | Work in 45 min batches
12:00 pm - 1:30 pm | Lunch / Walk / Bike / Workout
1:30 - 5:00 pm | Work in 45 min batches
5:00 pm to 8:00 pm | Kids/family
8:00 pm to 11:00 pm | Work in 45 min batches

## MVPFeatures
List of capabilities | Deadline | Relevant LangChain modules/solutions | Other Solutions outside langchain
- Set base knowledge of Hydrogen | 2023-07-15 | indexes, embeddings, vector stores | Pinecone, Estuary Flow
-- Need database of inputs and/or documents
- Read/input text from any PDF
- Build knowledge from each PDF. Retain that state.
- Verify with user whether output is accurate.
- Refine knowledge through user-input.
- Verify/vet/re-learn from user-input.
-- This must be able to cross-reference at least three other sources that come to similar conclusions
- Think like succesful energy investors
- Award tokens for flagging errors and suggesting new, community-accepted answers.
- Create an agent to respond to similar requests
- Agent-based game theory simulation
- Given string of questions, recommend further research, calculations, analysis.

## QuestionsFollowUp
1 | What to do when eval_chain.evaluate and QAEvalChain gives back INCORRECT answers?
2 | How to change the sources the LLM uses?

## HelpfulDocumentation
https://python.langchain.com/docs/modules/data_connection/
RetrievalQA works with both the vectorstores and the chain
- Keep text input to no more than 10-15 lines to control how many tokens being sent to LLM. -> should be vetted further.
"Agents" are a way to control what data is called when given prompt

## AdditionalFeatures
- Load transcripts from webpages, company websites, YouTube video transcripts
- Load private documents, analyze and keep queries proprietary

## UseCases
- High level understanding
- Run high level economics
- Understand/summarize policy
User Types:
- Analysts
- Directors
- C-suite
- Researchers
- Casual users

## Monetization
Market Segmentation:
- Casual User
- Advanced User
- Pro User
When signing people up, testing audience:
- Create artificial wait list when signing up
- Take credit card number when signing up. 14 days free trial period.